DakCUPAC Bourbon & Whiskey Tasting Fundraiser

CEO briefing  |  Target: Thursday evening, late summer / early fall 2026  |  Bismarck, ND

A private, 90-minute guided bourbon tasting for 40 CU executives, board members, and CU-affiliated PAC donors — led by Scott “Fuzzy” Meske. $250/ticket, six pours, engraved Glencairn glass gifted at check-in, Chick-fil-A catering. Net $8,500+ to PAC on $10,000 gross.

| GROSS REVENUE | GLASSWARE | CATERING | NET TO PAC |
| --- | --- | --- | --- |
| $10,000 40 × $250 | $763.20 48 engraved Glencairn @ $15.90 | $480 – $700 Chick-fil-A, spicy + non-spicy | $8,537 – $8,757 bottles, venue, Scott’s fee carried separately |

WHY IT WORKS

•  Right audience, right price. Credit union execs and board members are precisely the donor pool with room to give at the PAC contribution ceiling. $250 reads as a tasting ticket, not a fundraiser ask.

•  Sponsorships eat the biggest cost line. Six CU bottle sponsors cover the whiskey, so PAC keeps nearly all of the gate.

•  The glass is the marketing. Every attendee leaves with an engraved Glencairn that lives in their bar. DakCUPAC shows up every time they pour for the next decade.

SPONSORSHIP — SIX CU BOTTLE SPONSORS (~$500/BOTTLE)

•  Each sponsor: tent card next to their pour, verbal callout from Scott, logo on menu + check-in signage, two complimentary tickets (worth $500).

•  Optional Featured ND Pour sponsor underwrites a Heart River Spirits Painted Canyon (Bismarck craft distiller) host pour.

BOTTLE LINEUP — EACH BUYABLE TODAY AROUND $500

•  
        Michter’s 10 Yr Bourbon (2026) – $550  |  Old Forester Birthday 2025 – $700  |  Macallan 18 Sherry Oak – $412

•  Redbreast 21 Yr Irish – $400–500  |  Willett Family Estate 8 Yr – $300–550  |  Parker’s Heritage – $500+

GLASSWARE & CATERING

•  48 engraved Glencairn glasses at Sip n Savor — $15.90 each at the 48+ tier = $763.20. Spares cover breakage + late RSVPs.

•  Chick-fil-A catering at Kirkwood Mall Bismarck (701-751-0793, $175 delivery min): 2× Large Nugget Tray, classic + spicy sandwich trays, mac & cheese, fruit. Budget $480–$700.

TIMELINE

•  T-12: date + venue locked, Chick-fil-A quote secured.  T-10: sponsor outreach opens, glass artwork submitted.  T-8: sponsorships in.  T-3: glass delivery.  T-2: final headcount. Day-of: doors 5:30, tasting 6:00.

THE DECISION

•  Approve $250/40 anchor and ~$1,500 hard cost (glasses + catering) against $10K gross.

•  Green-light chair to open sponsor conversations with six CUs and book date with Scott.

•  Confirm venue lane: Elks Lodge #1199 (default) or a host residence if one volunteers.